## C&V Phase Analysis
C&V PHASE – INTERACTIVE COST ANALYSIS
1. BUDGET & SPEND
C&V budget | 81600 |  | From budget dashboard
C&V spend to date | 58970.25 |  | Latest dashboard – ECI corrections now included
Remaining budget (dashboard) | 22629.75
Remaining budget used for planning | 22600 |  | Rounded figure provided by Alycia
2. RATES
Alycia hourly rate | 263 |  | Provided by Alycia
Jeffrey hourly rate | 526 |  | Provided by Alycia
Past mix – Alycia share of time | 80% |  | Used only to estimate past hours
Past blended hourly rate | 315.6
3. PAST SPEND PER INTERACTIVE
Knowledge share days | 4
Hours per knowledge share day | 7
Knowledge share cost (at past blended rate) | 8836.8
Submissions supported to date | 2
Hours per submission (Alycia only) | 3 |  | Provided by Alycia
Submission cost to date | 1578
Spend on interactives only | 48555.45
Interactives supported to date | 8
Average cost per past interactive | 6069.4312
Average hours per past interactive | 19.2314 |  | Estimated at past blended rate
4. FUTURE COMMITMENTS
Upcoming submissions (GoFar request) | 3
Upcoming submission cost (Alycia only) | 2367
Budget available for interactives | 20233
5. FUTURE INTERACTIVE ASSUMPTIONS
Jeffrey hours per interactive | 0.75 |  | 45 minutes
Saving – no longer attending interactive | 4
Saving – no early admin/challenges | 1.5
Saving – no debrief document/guidance | 1
Planned hours per interactive | 10 |  | Alycia's estimate
6. HOW MANY MORE INTERACTIVES?
| Planned (10 hrs) | Based on past average
Total hours per interactive | 10 | 12.7314
Jeffrey hours | 0.75 | 0.75
Alycia hours | 9.25 | 11.9814
Cost per interactive | 2827.25 | 3545.6094
Interactives budget covers (exact) | 7.1564 | 5.7065
Interactives we can support (whole) | 7 | 5
Budget left over | 442.25 | 2504.9531
Legend: yellow cells with blue text are inputs – change them and everything recalculates. Shaded blue rows are key results.
Assumption: past hours are estimated using an 80/20 Alycia/Jeffrey mix, as the actual historic staff mix isn't known.
Future interactives assume Jeffrey contributes 45 minutes each and Alycia does the rest. Submissions are Alycia's time only.