## Slide 1
Supporting GoFar across the project
The Strategy Group
October 2026

## Slide 2
EOI • July
Interactive Preparation
Pre-C&V • September
Cultural Foundation Session
C&V Phase • Now
Early Interactives & Readiness
ECI Phase • 2027
Structured Interactive Phase
Our proposal indicates that we can provide support during the C&V and ECI Phase, but has not detailed support for the RFP phase
Completed
Ongoing
Upcoming
Completed
Pre-ECI • December
JV Alignment & Strategy Foundation Sessions
Upcoming
Our support will focus largely on the C&V and ECI Phase
Notes: Budget as contracted. Pre-ECI interactive preparation was reduced to $10,000 for goodwill and paid separately. The C&V Phase allocation is $81,600.

## Slide 3: The majority of our budget will be focused in the ECI Phase
Project steps | Investment (excl. GST)
Pre-ECI: Interactive Preparation | 
Virtual team introduction and alignment session | Reduced to $10,000 for goodwill (paid separately to this contract)
Pre-interactive team alignment session | 
Eight-step interactive preparation process | 
Presentation coaching | $15,000 ($5,000 each)
Foundation Sessions | 
Strategy to Win Workshop | $23,000
Culture Workshop | $23,000
Reflection and JV Alignment Workshop | $23,000
Interactive Readiness and Roleplay | $11,500
C&V Phase Support | 
Interactive readiness and debrief sessions | $81,600 (est. 14 sessions)
ECI Phase Support | 
Client interactive preparation and support | $174,000 (est. 12 sessions)
Ongoing Support | 
Strategy and Positioning Support | $37,000
Total | $388,100
PRE-ECI, FOUNDATION SESSIONS AND C&V PHASE
$177,100
45.6% of total budget
ECI PHASE
$211,000
54.4% of total budget
Notes: Budget as contracted. Pre-ECI interactive preparation was reduced to $10,000 for goodwill and paid separately. The C&V Phase allocation is $81,600.

## Slide 4: Four more interactives and three submissions
Our proposed support for the remainder of the C&V Phase, within the existing budget.
8
interactives supported
Capacity and Service through to Tunnel Requirements and AMF
4
further interactives
Alignment #4, Rolling Stock and Station Design #3, AMF and MMC, and Construction and Operational Staging
3
submissions
Two Alternate Alignment submissions (RFC#1659) and the Rolling Stock and Station Design wrap-up
We focus on preparation and rehearsal rather than attending interactives, which allows us to support the sessions that matter most.
Notes: Four further interactives and three submissions, delivered within the remaining C&V Phase budget. Alignment #4 is the priority, as the team needs to present updated designs for both the Baseline and the Alternate Alignment.

## Slide 5: The interactives we propose to support
We will focus on the sessions that most shape GoFar's final position: the alignment decision, station design and passenger experience, and how the project will be built and staged.
# | INTERACTIVE TOPIC | SESSION | DATE | STATUS
1 | Capacity and Service | Workshop 1 |  | Completed
2 | Alignment | Workshop 1 |  | Completed
3 |  | Workshop 3 |  | Completed
4 | Alternative Alignment | Workshop 2 |  | Completed
5 |  | Workshop 3 |  | Completed
6 | Fire and Life Safety | Workshop 2 |  | Completed
7 |  | Workshop 3 |  | Completed
8 | Tunnel Requirements and AMF | Workshop 2 |  | Completed
9 | Alignment (Baseline and Alternate) | Workshop 4 | Wed 4 Nov | Proposed
10 | Rolling Stock and Station Design | Workshop 3 | Thu 12 Nov | Proposed
11 | AMF and Modern Methods of Construction | Workshop 1 | Thu 12 Nov | Proposed
12 | Construction and Operational Staging | Workshop 1 | Tue 17 Nov | Proposed
+ | Submissions: Alternate Alignment (RFC#1659) | 2 submissions | 28 and 30 Oct | Proposed
+ | Submission: Rolling Stock and Station Design wrap-up | 1 submission | Thu 19 Nov | Proposed
Notes: Interactives 1 to 8 are complete. We propose to support four of the remaining sessions and three submissions. We have prioritised Alignment #4, where GoFar must present updated Baseline and Alternate Alignment designs, and the station design and construction methodology sessions, where GoFar's differentiation is strongest. RS&SD #3 and AMF and MMC run at the same time on 12 November and may be combined.

## Slide 6: Four lessons from the C&V Phase
LESSON
WHAT IT MEANS
IN PRACTICE
01
Preparation is paramount
Thorough preparation gives the team its key messages and puts GoFar in a strong light, even when slides are not presented.
In instances where GoFar doesn't present, the team is still better informed and ready because of the work done beforehand.
02
HSRA values guidance and capability
HSRA is looking for as much guidance as possible and responds to partners who bring structure and clarity.
In the Fire and Life Safety workshop, HSRA used GoFar's slides to run the meeting, as we had covered every point on its agenda.
03
Listening builds credibility
Responding to what HSRA has asked for, and building on its own work, earns more trust than innovation for its own sake.
The alternative alignment gained support because it built on HSRA's Business Case. Another partner's late, untested idea did not progress.
04
Our secret sauce: HSRA at the centre
Customer centricity sets GoFar apart. Every message starts with what HSRA needs, and we will keep building on it in the ECI.
By linking every point to HSRA's benefit, the alternative alignment became known as the GoFar alignment and gained other partners' support.
Notes: Lesson 1: in the 13 October session, a GoFar team member noted they knew far more than they would have without preparing. Lesson 2: after the 15 October Fire and Life Safety workshop, HSRA used GoFar's slides as the agenda. Lesson 3: the 6 October debrief noted GoFar built on HSRA's own work. Lesson 4: customer centricity is the thread through all of these, and the one to keep building on in the ECI.

## Slide 7: What we have heard and seen through the C&V Phase
The JV has made strong progress. A few changes now will set the team up well for the ECI Phase.
WHAT IS WORKING
Context before the solution
Framing each idea around HSRA's needs made complex proposals easy to support.
Clear, simple messages
Distilling technical material into a few client-relevant points helped HSRA adopt our thinking.
A strong presence
Engaged, consistent body language made GoFar visibly the strongest ECI partner.
WHAT NEEDS TO CHANGE BEFORE THE ECI
A one-team culture
The team works well together, but nothing yet ties the JV together as one team. The move to 100 Arthur Street is a great first step; a shared activity outside the office would help solidify that culture.
Front-loaded preparation
Day-before prep sessions leave little room to change anything and lead to late nights. In our approach, content is locked two days out, leaving the final two days for rehearsal and minor tweaks. This should be the ECI standard.
One agreed position
Share a weekly update on the latest design position, and raise concerns early rather than defaulting to yes.
Focus and continuity
Track HSRA's requests in one place, keep consistent faces across sessions, and present a few focused slides with detail in reserve.
For discussion: What else have you seen that we should address before the ECI Phase?
Notes: Drawn from conversations with the team and the October preparation and debrief sessions. Use this slide to open the floor before moving to the proposed December workshops.

## Slide 8: Two workshops to realign the team before the ECI Phase
The ECI Phase will be decisive. We will reflect on what we have learned about ourselves, HSRA, the other ECI partners and the process, and enter the ECI as one team with a clear strategy.
01
Reflection and JV Alignment Workshop
Reflecting through an external and an internal lens
External lens
What we now know about HSRA, its priorities and how it assesses partners
Internal lens
How the JV has worked together, and the culture and ways of working needed for 2027
Outcome
A shared view of HSRA, a one-team mindset and agreed ways of working
02
Strategy to Win Workshop
Defining how GoFar will compete in the ECI Phase
Positioning
Win themes and GoFar's unique selling proposition
Competitors
A map of the other ECI partners, their strengths and likely approach
Outcome
A clear ECI strategy and key messages
Notes: Funded from the Foundation Sessions allocation. These sessions respond directly to what we have heard: building a one-team culture, agreeing how the JV works together in the ECI, and entering the ECI with a clear strategy. We can shape the format and length around the team's availability in December.

## Slide 9: We have allowed for 12 interactives in the ECI phase
An estimated 12 interactives, each following our eight-step process, with TSG in the room for live support. This is where our most intensive support will be provided, where HSRA looks for evidence that GoFar has listened, adapted and grown.
PREPARE
DEVELOP
REHEARSE
DELIVER
Content discussion and objective-setting session
Align on the interactive's purpose, format and the outcomes the JV needs to achieve
Informal alignment with team
Hold catch-ups with individuals to assist with content development, and personal delivery style
Presentation development and refinement
Shape the narrative arc, structure and key messages that will resonate with HSRA evaluators
First rehearsal and structured debrief
Run a full dry-run and identify what's working, what needs sharpening and where confidence gaps sit
Workshop attendance and live support
Attend alongside the team to read the room and provide real-time strategic support
Talking points and speaker guide development
Craft individual speaker notes that feel natural, not scripted
Final rehearsal and refinement
Stress-test the full presentation under realistic conditions and lock in the final version
Post-interactive debrief session
Capture what worked, what to take forward and how the team performed against its objectives
1
2
3
4
5
6
7
8
Notes: For the final submission interactives we add a deep content review against everything HSRA has said, asked and signalled, narrative calibration to show GoFar has listened and adapted, and intensive rehearsal with TSG attending live.